## Sheet1
Sequence | Code | StoryTitle | Category | Phase | Status | Comment
1 | PS-01 | PS — Create Partner (Single) with Cryptographic Intake Receipt (CIR) | PS | Phase 1 — Partner Store Essentials | completed | Have to test
2 | PS-02 | PS — Bulk Upload with Row Receipts & Partial Commit | PS | Phase 1 — Partner Store Essentials | completed | Have to test
3 | PS-03 | PS — Duplicate Guardian & Safe Merge | PS | Phase 1 — Partner Store Essentials | impleemnted | Have to test
4 | PS-04 | PS — Update (Idempotent) with Auto-Rescreen Hooks | PS | Phase 1 — Partner Store Essentials
5 | PS-05 | PS — Status Lifecycle: Deactivate/Archive/Reactivate | PS | Phase 1 — Partner Store Essentials
6 | PS-06 | PS — Partner Screening Linkage & Lineage | PS | Phase 1 — Partner Store Essentials
7 | PS-07 | PS — Alerts, Cases & Transaction Linkage | PS | Phase 1 — Partner Store Essentials
8 | PS-08 | PS — Search, Filter, Bulk Actions | PS | Phase 1 — Partner Store Essentials
9 | PS-09 | PS — ERP/CRM/E-com Sync (Push/Pull) | PS | Phase 2 — Integrations & Privacy
10 | PS-10 | PS — Privacy & Sensitive IDs | PS | Phase 2 — Integrations & Privacy
11 | PS-11 | PS — Risk Score & Watchlist Subscriptions | PS | Phase 2 — Integrations & Privacy
12 | PS-12 | PS — Ownership & UBO Graph with Cascade Screening | PS | Phase 3 — Advanced Partner Governance
13 | PS-13 | PS — Relationship & Sites Model (sold-to/ship-to/bill-to) | PS | Phase 3 — Advanced Partner Governance
14 | PS-14 | PS — KYC Pack & Attestations (with Renewals) | PS | Phase 3 — Advanced Partner Governance
15 | PS-15 | PS — Internal Lists (Restricted/Watch/Preferred) | PS | Phase 3 — Advanced Partner Governance
16 | PS-16 | PS — External Identity Enrichment (LEI/DUNS/VAT) | PS | Phase 3 — Advanced Partner Governance
17 | PS-17 | PS — Rescreen Cadence & Activity Triggers | PS | Phase 3 — Advanced Partner Governance
18 | PS-18 | PS — Case SLA & Escalation Matrix | PS | Phase 3 — Advanced Partner Governance
19 | PS-19 | PS — Partner Self-Service Portal (optional) | PS | Phase 4 — Tenant Customization & Global Support
20 | PS-20 | PS — Data Quality Score & Auto-Coach | PS | Phase 4 — Tenant Customization & Global Support
21 | PS-21 | PS — Partner Store API & Webhooks (v1) | PS | Phase 4 — Tenant Customization & Global Support
22 | PS-22 | PS — Custom Fields & Validation (per-tenant) | PS | Phase 4 — Tenant Customization & Global Support
23 | PS-23 | PS — Global Names & Addresses (i18n + transliteration) | PS | Phase 4 — Tenant Customization & Global Support
24 | PS-24 | PS — Bulk Change Review & Undo | PS | Phase 4 — Tenant Customization & Global Support
25 | OPS-01 | OPS-01 — Owners & SLOs for PS-12…PS-24 (planning infusion) | OPS | Phase 5 — Ops Locks (Foundational)
26 | OPS-02 | OPS-02 — Accessibility Hardening (WCAG 2.2 AA) | OPS | Phase 5 — Ops Locks (Foundational)
27 | OPS-03 | OPS-03 — Performance & Load Plan | OPS | Phase 5 — Ops Locks (Foundational)
28 | OPS-04 | OPS-04 — UAT Checklist + Seed Data | OPS | Phase 5 — Ops Locks (Foundational)
29 | OPS-05 | OPS-05 — Telemetry & Dashboards | OPS | Phase 5 — Ops Locks (Foundational)
30 | OPS-06 | OPS-06 — Security Drills (Pen-Test + Override Trail) | OPS | Phase 5 — Ops Locks (Foundational)
31 | OPS-07 | OPS-07 — Docs & Examples (PS-21 API) | OPS | Phase 5 — Ops Locks (Foundational)
32 | OPS-08 | OPS-08 — Feature Flags & Kill-Switches | OPS | Phase 5 — Ops Locks (Foundational)
33 | OPS-09 | OPS-09 — Threat Modeling & Secure Design Review (STRIDE before GA) | OPS | Phase 6 — Ops & Governance (Extended)
34 | OPS-10 | OPS-10 — SSO/SAML & SCIM (Enterprise Access) | OPS | Phase 6 — Ops & Governance (Extended)
35 | OPS-11 | OPS-11 — Data Residency & Sovereignty Controls | OPS | Phase 6 — Ops & Governance (Extended)
36 | OPS-12 | OPS-12 — Schema & Data Migration Playbooks (Zero Downtime) | OPS | Phase 6 — Ops & Governance (Extended)
37 | OPS-13 | OPS-13 — Event Schema Registry & Contract Tests | OPS | Phase 6 — Ops & Governance (Extended)
38 | OPS-14 | OPS-14 — Chaos / Failure Injection (Gate & Webhooks) | OPS | Phase 6 — Ops & Governance (Extended)
39 | OPS-15 | OPS-15 — FinOps & Cost Guardrails | OPS | Phase 6 — Ops & Governance (Extended)
40 | OPS-16 | OPS-16 — DSAR (Access/Export) Workflow | OPS | Phase 6 — Ops & Governance (Extended)
41 | OPS-17 | OPS-17 — Admin & Support Tooling (Resolve Without Engineering) | OPS | Phase 6 — Ops & Governance (Extended)
42 | OPS-18 | OPS-18 — Secrets/Keys Rotation Runbook (Zero Downtime) | OPS | Phase 6 — Ops & Governance (Extended)
43 | ADD-01 | ADD-01 — DPIA & Regulatory Mapping (GDPR/CCPA + Export Controls) | ADD | Phase 7 — Optional Add-ons
44 | ADD-02 | ADD-02 — Incident Response & Breach Notification Runbook | ADD | Phase 7 — Optional Add-ons
45 | ADD-03 | ADD-03 — Provider SLA & Feed Integrity Monitor | ADD | Phase 7 — Optional Add-ons
46 | ADD-04 | ADD-04 — Tenant Onboarding & Migration Toolkit | ADD | Phase 7 — Optional Add-ons
47 | ADD-05 | ADD-05 — Client SDKs & Samples (PS-21 + Screening/Gate APIs) | ADD | Phase 7 — Optional Add-ons
48 | ADD-06 | ADD-06 — Browser/Device Matrix & Non-JS Fallbacks | ADD | Phase 7 — Optional Add-ons
49 | ADD-07 | ADD-07 — Release Notes & Change Management | ADD | Phase 7 — Optional Add-ons
50 | ADD-08 | ADD-08 — Billing/Entitlements & Usage Plans | ADD | Phase 7 — Optional Add-ons
51 | ADD-09 | ADD-09 — Config Promotion & Secrets Hygiene (Dev→Stage→Prod) | ADD | Phase 7 — Optional Add-ons
52 | ADD-10 | ADD-10 — Data Catalog & Lineage Explorer | ADD | Phase 7 — Optional Add-ons
53 | ADD-11 | ADD-11 — Consent & Preference Center (if needed) | ADD | Phase 7 — Optional Add-ons
54 | ADD-12 | ADD-12 — Customer-Managed Keys (CMK) Option | ADD | Phase 7 — Optional Add-ons
55 | CERT-01 | CERT-01 — Independent Certifications Pack (ISO 27001 / SOC 2 Binder) | PACKAGING/LAUNCH | Phase 8 — Final Packaging & Launch
56 | AI-01 | AI-01 — AI Governance for Assistive Features (Advisory-Only, HIL) | PACKAGING/LAUNCH | Phase 8 — Final Packaging & Launch
57 | LAUNCH-01 | LAUNCH-01 — Go-Live & Cutover Runbook (Hypercare + Rollback) | PACKAGING/LAUNCH | Phase 8 — Final Packaging & Launch
58 | SALES-01 | SALES-01 — Customer Procurement Bundle (One-Click) | PACKAGING/LAUNCH | Phase 8 — Final Packaging & Launch
59 | OPS-19 | BCP/DR & RTO/RPO — “Failover That Proves Itself” | OPS | Phase 5 — Ops Locks (Foundational)
60 | OPS-20 | Tenant Data Retention Matrix — “Hot/Warm/Archive + Legal Holds” | OPS | Phase 5 — Ops Locks (Foundational)
61 | OPS-21 | API Contracts v1 (OpenAPI) — “Stable Pipes with Receipts” | OPS | Phase 5 — Ops Locks (Foundational)
62 | OPS-22 | Rate Limits & Tiering — “Fair, Burst-Friendly, and Honest” | OPS | Phase 5 — Ops Locks (Foundational)
63 | OPS-23 | Localization & Time Zones — “Decisions That Read Like Home” | OPS | Phase 5 — Ops Locks (Foundational)
64 | OPS-24 | Access Reviews & Segregation of Duties (SoD) — “Trust, Re-attested” | OPS | Phase 5 — Ops Locks (Foundational)